## README
Cost and Pricing Model
Document 05 of the proposal package. Every number on the calculation sheets is a formula driven by the Assumptions sheet.
HOW TO USE
1. Change only BLUE cells on the Assumptions and Rate_Card sheets. Black cells are formulas; green cells link to other sheets.
2. Yellow-filled cells are the key commercial levers to agree with the client: blended rate, support tier, and the deployment pattern per tier.
3. Run_Cost_by_Tier shows monthly operating cost for four tiers (pilot to group scale). Build_Effort shows role effort and fees per phase. Pricing_Options shows the three commercial structures. TCO_3yr adds them up.
4. Prices are 2026 list prices from public pricing pages (see Sources column and comments). They change; confirm before quoting.
COLOUR LEGEND
Blue text = input you may change. Black text = formula. Green text = link from another sheet. Yellow fill = key assumption to agree with the client.
SHEETS
Assumptions: volumes, prices, and unit costs. Rate_Card: roles and rates. Run_Cost_by_Tier: monthly run cost. Build_Effort: fees by phase. Pricing_Options: commercial structures. TCO_3yr: three-year view.
IMPORTANT
Run cost excludes build fees. Build fees exclude cloud and AI usage, which are passed through at cost from the client's own accounts. All figures in USD, excluding VAT.

## Assumptions
Assumptions and unit prices
Blue = inputs. Tier columns: 0 Pilot, 1 Departmental, 2 Enterprise/Sovereign, 3 Group-scale.
Volume driver | Tier 0 Pilot | Tier 1 Dept | Tier 2 Enterprise | Tier 3 Group | Unit | Notes / source
Named users | 10 | 50 | 300 | 1500 | users | Client to confirm in discovery
Documents in corpus (cumulative) | 2000 | 25000 | 250000 | 1500000 | docs | Indicative; pilot limit 5,000 in SOW
Average pages per document | 20 | 20 | 20 | 20 | pages | Contracts and reports; spreadsheets counted by sheet
Tokens per page | 600 | 600 | 600 | 600 | tokens | Roughly 450 words per page
Share of pages that are scans needing OCR | 30% | 30% | 30% | 30% | % | GCC corpora often have many scanned Arabic pages
New documents per month (share of corpus) | 5% | 5% | 5% | 5% | % | Ongoing ingestion after initial load
Questions per user per working day | 5 | 5 | 4 | 3 | questions | Executives ask fewer, analysts more
Working days per month | 22 | 22 | 22 | 22 | days
Input tokens per question (retrieved passages + prompt) | 12000 | 12000 | 12000 | 12000 | tokens | 8-12 passages of 400-600 tokens plus instructions
Output tokens per question (answer + citations + grounding pass) | 1500 | 1500 | 1500 | 1500 | tokens | Includes the second grounding pass
Share of questions answered by Opus 5 (rest Sonnet 5) | 40% | 40% | 40% | 40% | % | Complex questions and contradiction adjudication
Extraction tokens per page (claims pass, Sonnet 5) | 900 | 900 | 900 | 900 | tokens | Input page tokens + structured output
Prompt-cache and batch discount on ingestion | 40% | 40% | 40% | 40% | % | Batch API 50% off; caching on shared prefixes
Outreach messages per month (CRM) | 200 | 1500 | 8000 | 40000 | messages | Email mostly; WhatsApp priced separately
Share of AI-assisted drafts | 50% | 50% | 50% | 50% | %
Tokens per AI-assisted draft (in + out) | 4000 | 4000 | 4000 | 4000 | tokens | Sonnet 5
Deployment pattern (A cloud, B hybrid, C sovereign) | A | B | C | C | pattern | Key lever: C adds GPU cost and removes most API cost
Share of AI processing routed in-region under pattern B | 0% | 30% | 100% | 100% | % | Set to 1 for pattern C
GPU nodes for in-region models (0 if pattern A) | 0 | 1 | 4 | 20 | nodes | Each node ~ 1x H100-class 80GB; two for HA at tier 2+
Unit price (2026 list) | Price |  |  |  | Unit | Source
Claude Opus 5 input | 5 |  |  |  | USD / M tokens | Anthropic pricing, 2026 (claude-opus-5)
Claude Opus 5 output | 25 |  |  |  | USD / M tokens | Anthropic pricing, 2026
Claude Sonnet 5 input | 2 |  |  |  | USD / M tokens | Anthropic pricing, 2026 (claude-sonnet-5)
Claude Sonnet 5 output | 10 |  |  |  | USD / M tokens | Anthropic pricing, 2026
Voyage voyage-3.5 embeddings | 0.02 |  |  |  | USD / M tokens | Voyage AI pricing page, 2026; first 200M tokens free
Voyage rerank-2.5 | 0.05 |  |  |  | USD / M tokens | Voyage AI pricing page, 2026; verify current rate
OCR (Azure AI Document Intelligence, read/layout) | 1.5 |  |  |  | USD / 1,000 pages | Azure pricing, UAE North; verify current rate
Supabase Pro (pilot database, storage, auth) | 25 |  |  |  | USD / month | supabase.com/pricing, 2026, plus usage
Vercel Pro (pilot web hosting) | 20 |  |  |  | USD / seat / month | vercel.com/pricing, 2026
Managed PostgreSQL in GCC region, tier 1 | 400 |  |  |  | USD / month | AWS RDS / Azure Database, mid-size instance with storage; estimate
Managed PostgreSQL in GCC region, tier 2 (HA) | 2500 |  |  |  | USD / month | Multi-AZ, larger instance, PITR; estimate
Managed PostgreSQL in GCC region, tier 3 (HA, read replicas) | 9000 |  |  |  | USD / month | Estimate
Containers, load balancer, storage, networking, tier 1 | 600 |  |  |  | USD / month | ECS/Fargate or Container Apps; estimate
Containers, load balancer, storage, networking, tier 2 | 4000 |  |  |  | USD / month | Kubernetes or managed containers, HA; estimate
Containers, load balancer, storage, networking, tier 3 | 18000 |  |  |  | USD / month | Multi-tenant, DR region; estimate
GPU node (H100-class 80GB) in-region, on-demand | 4.5 |  |  |  | USD / hour | Hyperscaler GCC region on-demand; reserved pricing 30-50% lower; verify
Hours per month | 730 |  |  |  | hours
Observability, security tooling, backups, tier 1 | 300 |  |  |  | USD / month | Langfuse cloud or self-host, Sentry, WAF; estimate
Observability, security tooling, backups, tier 2 | 2000 |  |  |  | USD / month | Plus SIEM export, KMS, pen-test amortised; estimate
Observability, security tooling, backups, tier 3 | 8000 |  |  |  | USD / month | Estimate
Email sending (Graph/Gmail) per message | 0 |  |  |  | USD | Included in the client's Microsoft 365 / Google licences
WhatsApp Business conversation (utility) | 0.03 |  |  |  | USD / conversation | Meta per-conversation pricing varies by country; verify
Share of outreach via WhatsApp | 10% |  |  |  | % | Assumption

## Rate_Card
Rate card and blended rate
Blue = inputs. Rates are indicative ranges by delivery location; set the yellow blended rate for the quote.
Role | Weekly rate (USD) | Daily rate (USD) | Hourly rate (USD) | Guidance
Engagement lead / solution architect | 6000 | 1200 | 150 | Senior; sets architecture and quality gate
AI engineer (Python) | 4500 | 900 | 112.5 | Retrieval, extraction, evaluation
Full-stack engineer (TypeScript) | 4000 | 800 | 100 | Web app, Core API, CRM workflow
QA and evaluation analyst | 2500 | 500 | 62.5 | Golden set, tests, acceptance
Project manager | 3000 | 600 | 75 | Plan, risks, client reporting
UX designer | 3000 | 600 | 75 | Interface, Arabic layout
Security and DevOps specialist | 4500 | 900 | 112.5 | IaC, hardening, pen-test coordination
Blended weekly rate used for fees (set this) | 3928.5714 |  |  | Indicative market ranges per person-week (2026): South Asia 1,000-2,000; Eastern Europe 2,500-4,500; GCC-based / UK / US 5,000-9,000. Set rates to match your delivery model.
Managed service: support tier as share of annual platform fee | 20%
Managed service: annual platform fee as share of build fees (M0-M4) | 18%
Note on B13: Default is the simple average of the rate card. Override with an agreed blended rate (type a number over the formula) if the client prefers a single rate.
Note on B14: Standard 15%, Business 20%, Enterprise 30% of the annual platform fee.
Note on B15: Covers upgrades, model changes, evaluation re-runs, minor enhancements. Typical range 15-22% of build.

## Run_Cost_by_Tier
Monthly run cost by tier (USD)
All cells are formulas. Initial ingestion is a one-off shown separately; monthly figures include ongoing ingestion of new documents.
Line | Tier 0 Pilot | Tier 1 Dept | Tier 2 Enterprise | Tier 3 Group | How it is calculated
Corpus pages | 40000 | 500000 | 5000000 | 30000000 | documents x pages per document
Questions per month | 1100 | 5500 | 26400 | 99000 | users x questions per day x working days
ONE-OFF: initial ingestion, embeddings | 0.48 | 6 | 60 | 360 | corpus tokens x embedding price (first 200M tokens free, not netted)
ONE-OFF: initial ingestion, OCR of scanned pages | 18 | 225 | 2250 | 13500 | scanned pages x OCR price per 1,000
ONE-OFF: initial ingestion, claims extraction (Sonnet 5, batch) | 86.4 | 756 | 0 | 0 | pages x extraction tokens x blended Sonnet price x (1 - discount) x share via API
ONE-OFF: initial ingestion total | 104.88 | 987 | 2310 | 13860
Monthly: ongoing ingestion (share of corpus per month) | 5.244 | 49.35 | 115.5 | 693 | one-off total x monthly new-document share
Monthly: question answering, Opus 5 share | 42.9 | 150.15 | 0 | 0 | questions x Opus share x (in tokens x price + out tokens x price)
Monthly: question answering, Sonnet 5 share | 25.74 | 90.09 | 0 | 0 | as above for Sonnet
Monthly: re-ranking | 1.1 | 5.5 | 26.4 | 99 | questions x 40 candidates x 500 tokens x rerank price
Monthly: CRM AI-assisted drafts (Sonnet 5) | 2.08 | 10.92 | 0 | 0 | messages x AI share x tokens x blended price
Monthly: WhatsApp conversations | 0.6 | 4.5 | 24 | 120 | messages x WhatsApp share x per-conversation price
Monthly: AI and messaging subtotal | 77.664 | 310.51 | 165.9 | 912
Monthly: database and storage | 25 | 400 | 2500 | 9000 | Supabase Pro at pilot; managed PostgreSQL in region above
Monthly: application hosting | 100 | 600 | 4000 | 18000 | Vercel Pro (2 seats) + small container at pilot; containers in region above
Monthly: in-region GPU nodes (patterns B/C) | 0 | 3285 | 13140 | 65700 | nodes x hourly price x hours; reserved pricing can cut this 30-50%
Monthly: observability, security tooling, backups | 40 | 300 | 2000 | 8000 | Sentry/Langfuse free tiers at pilot
Monthly: infrastructure subtotal | 165 | 4585 | 21640 | 100700
MONTHLY RUN COST TOTAL | 242.664 | 4895.51 | 21805.9 | 101612 | AI and messaging + infrastructure
Annual run cost | 2911.968 | 58746.12 | 261670.8 | 1219344
Run cost per named user per month | 24.2664 | 97.9102 | 72.6863 | 67.7413 | guards against zero users
Note: one-off ingestion (row 10) is paid once at load and again only for re-indexing; it is excluded from the monthly total. Pilot totals sit within the USD 150-400 per month range quoted in the deck when the volume drivers are at the Tier 0 defaults.

## Build_Effort
Build effort and fees by phase
Blue = person-weeks per role per phase (inputs). Fees = person-weeks x blended weekly rate from Rate_Card.
Role | Phase 0 Discovery | Phase 1 Foundation | Phase 2 Verification + approval | Phase 3 Pilot | Phase 4 Production | Total weeks | Fee (USD)
Engagement lead / solution architect | 1 | 2.5 | 2 | 2.5 | 2 | 10 | 39285.7143
AI engineer (Python) | 1 | 5 | 4 | 6 | 3 | 19 | 74642.8571
Full-stack engineer (TypeScript) | 0.5 | 5 | 4 | 5 | 3 | 17.5 | 68750
Second engineer (AI or full-stack) | 0 | 1 | 4 | 4 | 3 | 12 | 47142.8571
QA and evaluation analyst | 0.5 | 1.5 | 2 | 3 | 2 | 9 | 35357.1429
Project manager | 0.6 | 1.5 | 1.2 | 1.8 | 1.5 | 6.6 | 25928.5714
UX designer | 0.4 | 1.2 | 0.6 | 0.4 | 0.2 | 2.8 | 11000
Security and DevOps specialist | 0.4 | 0.8 | 0.6 | 0.8 | 2 | 4.6 | 18071.4286
Total person-weeks | 4.4 | 18.5 | 18.4 | 23.5 | 16.7 | 81.5 | 320178.5714
Fee per phase (USD) | 17285.7143 | 72678.5714 | 72285.7143 | 92321.4286 | 65607.1429 |  | 320178.5714
Contingency on build (share) | 10%
Total build fees including contingency (M0-M4) | [6 empty] | 352196.4286
Calendar duration by phase (weeks) | 2 | 5 | 4 | 6 | 5 | 22 | Phases overlap; elapsed timeline is 20 weeks
Average team size (FTE) by phase | 2.2 | 3.7 | 4.6 | 3.9167 | 3.34
Milestone payment schedule (from Pricing structure in Document 14)
Milestone | Basis | [5 empty] | Amount (USD)
M0 Discovery complete (week 2) | 100% of Phase 0 | [5 empty] | 19014.2857
On signature of Phases 1-2 | 40% of Phases 1-2 | [5 empty] | 63784.2857
M1 Working structure (week 6) | 30% of Phases 1-2 | [5 empty] | 47838.2143
M2 Integrated demo (week 9) | 30% of Phases 1-2 | [5 empty] | 47838.2143
M3 Pilot exit (week 15) | 100% of Phase 3 | [5 empty] | 101553.5714
M4 Production go-live (week 20) | 100% of Phase 4 | [5 empty] | 72167.8571
Total (equals build fees incl. contingency) | [6 empty] | 352196.4286
Check: difference to build total (should be 0) | [6 empty] | 0
Note on B15: Applied to fixed-price phases to cover scope discovery. 10-15% is typical.

## Pricing_Options
Commercial structures
Three ways to contract the same scope. Figures link to Build_Effort, Rate_Card and Run_Cost_by_Tier.
Option A: Fixed price by milestone (recommended) | USD | Notes
Build fees, M0-M4, including contingency | 352196.4286
Annual managed service: platform fee | 63395.3571 | Share of build fees per year; covers upgrades, model changes, evaluation re-runs, minor enhancements
Annual managed service: support tier | 12679.0714 | Standard 15%, Business 20%, Enterprise 30% of platform fee (set on Rate_Card)
Annual managed service total (excluding pass-through cloud and AI) | 76074.4286
Pass-through run cost, year 1, at the selected tier (see TCO_3yr) | 58746.12
Option B: Time and materials with monthly cap | USD | Notes
Blended weekly rate | 3928.5714
Planned person-weeks (from Build_Effort) | 81.5
Monthly cap (person-weeks x rate / months) | 64035.7143 | Assumes 20 weeks = 5 months; client pays actuals up to the cap
Expected total at plan (no contingency needed) | 320178.5714
Suitable when scope is expected to evolve during the pilot; risk sits with the client, so the rate is typically 5-10% lower than fixed-price equivalents.
Option C: Subscription (build amortised into an annual fee) | USD | Notes
Contract term (years) | 3
Financing uplift on amortised build | 12% | Compensates for deferred payment and cancellation risk
Annual subscription = build x (1+uplift) / term + managed service | 207561.0952
Lower entry cost for the client; total over the term is higher than Option A. Code ownership can still transfer at end of term or on early buy-out.
Smaller starting scopes (fixed price) | USD | Notes
Discovery only (Phase 0) | 19014.2857
Discovery + System 1 working structure only | 62984.8214 | Platform layer plus assistant; CRM deferred. 55% of Phase 1 effort.
Discovery + CRM for one category only | 58987.5 | Platform layer plus CRM; assistant deferred. 50% of Phase 1 effort.
Clickable prototype at week 4 (add-on to Phase 1) | 5892.8571 | About 1.5 person-weeks of demo preparation

## TCO_3yr
Three-year total cost of ownership
Choose the tier path in the blue cells. Build fees in year 1; managed service and run cost every year; optional Phase 5 scale-out budget.
Item | Tier in year | Year 1 | Year 2 | Year 3 | Notes
Tier operated in each year (0-3) |  | 1 | 2 | 2 | Typical path: pilot then departmental in year 1, enterprise from year 2
Build fees (M0-M4) |  | 352196.4286 | 0 | 0
Managed service (platform fee + support) |  | 38037.2143 | 76074.4286 | 76074.4286 | Half year in year 1 (go-live at week 20)
Run cost (pass-through cloud and AI) at the year's tier |  | 58746.12 | 261670.8 | 261670.8 | INDEX into annual run cost by tier
One-off initial ingestion at the year's tier (re-index on tier change) |  | 987 | 2310 | 0
Phase 5 scale-out budget (connectors, sovereign switch, integrations) |  | 0 | 31428.5714 | 23571.4286 | Person-weeks x blended rate; adjust to roadmap
TOTAL PER YEAR |  | 449966.7629 | 371483.8 | 361316.6571
THREE-YEAR TOTAL |  | 1182767.22
Reading the result: the client sees a single build investment in year 1, a predictable managed-service fee, and run costs that scale with the tier they choose. Build fees do not recur when moving up a tier; only run cost and, if chosen, Phase 5 work change.