## Risk_Register
Risk Register
Score = Likelihood x Impact (1-5 each). Rating: 15+ High, 8-14 Medium, under 8 Low. Blue cells are inputs; update at each steering call.
ID | Category | Risk | Likelihood (1-5) | Impact (1-5) | Score | Rating | Mitigation | Owner | Trigger / early indicator | Status
R01 | Data and compliance | Client's legal team requires that no document text leaves the country, making Pattern A unusable for the pilot | 3 | 4 | 12 | Medium | Settle residency in discovery (week 1); gateway supports in-region routing; sovereign pattern designed and priced; keep a small in-region model available for restricted classes | Engagement lead | Legal review outcome at discovery | Open
R02 | Data and compliance | Personal data of investors and contacts stored or contacted without a lawful basis under Saudi or UAE PDPL | 3 | 5 | 15 | High | Consent and lawful-basis fields per contact; outreach flag when consent missing; data protection checkpoint before real data; legal confirms basis per jurisdiction | Client legal + PM | Missing consent rate in import preview | Open
R03 | Data and compliance | Frontier model availability or terms in GCC regions change during the project (cross-region inference, retention terms) | 3 | 3 | 9 | Medium | Model gateway abstracts providers; re-verify availability at discovery and before go-live; open-weight fallback evaluated in Phase 3 | AI engineer | Provider announcements; failed region checks | Open
R04 | Accuracy | Claims extraction precision below target on messy scanned or Arabic documents | 4 | 4 | 16 | High | Sample corpus in week 1 includes worst cases; OCR with layout analysis; confidence thresholds route low-confidence extractions to human review; tune prompts and tolerances in pilot | AI engineer | Labelled-sample precision below 90% at week 6 | Open
R05 | Accuracy | False-positive contradiction flags erode trust (superseded drafts, rounding, currency) | 4 | 3 | 12 | Medium | Version detection and supersedes links; numeric tolerance and currency normalisation; adjudication pass with rationale; dismiss-with-reason feeds tuning; both quotes always shown | AI engineer | False-positive rate above 15% in pilot | Open
R06 | Accuracy | Answers hallucinate or cite the wrong page | 2 | 5 | 10 | Medium | Grounding check removes unsupported sentences; refusal when nothing survives; citation accuracy in golden set; regression gate in CI | AI engineer | Citation accuracy below 95% | Open
R07 | Scope | Decision types and evidence checklists not defined by the client, so gap tracking cannot be demonstrated | 3 | 4 | 12 | Medium | Two discovery sessions dedicated to decision types; start with five; template library of common decisions as a fallback | Product owner | No catalogue by end of week 2 | Open
R08 | Scope | Scope creep: additional connectors, ERP integration, mobile app requested during pilot | 4 | 3 | 12 | Medium | Change control with impact on time and cost; Phase 5 roadmap holds requests; sponsor approves changes | PM | Requests outside SOW at steering | Open
R09 | Delivery | Late client inputs (sample documents, identity access, mailbox consent) delay milestones | 4 | 3 | 12 | Medium | Dependency list with dates; weekly steering; timeline extends by the delay per SOW; IT contact named at kick-off | PM + client IT | Dependency overdue by 5 days | Open
R10 | Delivery | Key engineer unavailable mid-project | 2 | 4 | 8 | Medium | Documented code and architecture; two engineers share knowledge from week 5; supplier bench cover | Engagement lead | Absence notice | Open
R11 | Delivery | Underestimated effort for Arabic right-to-left interface and bilingual search | 3 | 3 | 9 | Medium | Arabic in scope from Phase 1, not retrofitted; UX designer on Arabic layout; per-language evaluation | Full-stack engineer | Arabic golden-set scores lag English by more than 10 points | Open
R12 | Security | Prompt injection via a malicious or crafted document changes assistant behaviour | 2 | 4 | 8 | Medium | Retrieved text treated as data with delimiters; injection-pattern flags at ingestion; no tool actions from the assistant; penetration test includes injection cases | Security specialist | Injection test failures | Open
R13 | Security | Access control mis-configuration exposes restricted documents to unauthorised users | 2 | 5 | 10 | Medium | Row-level security in database; ACL mirrored from source; permission tests in CI; access review at go-live | Security specialist | Failed permission test; audit anomaly | Open
R14 | Security | Staff bypass the approval gate by sending from personal mailboxes | 3 | 2 | 6 | Low | Policy plus reporting of approved-route sends; connected mailbox captures replies; management review of outreach volumes | Client compliance | Outreach volumes drop while replies rise | Open
R15 | Cost | AI usage costs exceed pilot budget due to heavy re-indexing or long documents | 2 | 2 | 4 | Low | Gateway budgets and alerts; batch and caching on ingestion; Sonnet for routine questions; monthly usage report | AI engineer | Spend above 120% of forecast | Open
R16 | Cost | Sovereign GPU hosting cost higher than modelled or capacity unavailable in region | 3 | 3 | 9 | Medium | Reserved pricing; right-size model (smaller open-weight model for routine tasks); decide after pilot with measured usage | Engagement lead | Quotes above model by more than 25% | Open
R17 | Adoption | Relationship managers do not log interactions, so reporting and reminders are unreliable | 4 | 4 | 16 | High | Pilot champions; mailbox and calendar capture reduce manual logging; simple mobile-friendly forms; management uses the dashboards visibly | Product owner | Interactions logged per user per week below target | Open
R18 | Adoption | Executives lose trust after an early wrong answer | 3 | 4 | 12 | Medium | Set expectations: cited, checkable answers; show refusals as a feature; weekly accuracy reporting; feedback button on every answer | Engagement lead | Usage drop after an incident | Open
R19 | Vendor | Third-party service (embedding, OCR, hosting) price or terms change | 2 | 2 | 4 | Low | All components swappable; alternatives listed in Document 06; contracts in the client's name | PM | Vendor notice | Open
R20 | Commercial | Client expects a single fixed price before discovery | 3 | 3 | 9 | Medium | Present tiers and structure; offer fixed price for discovery and demo; workbook transparency | Engagement lead | Procurement asks for a total before week 0 | Open
R21 | Operational | Production incident without an on-call arrangement in the departmental tier | 2 | 3 | 6 | Low | Support tier chosen before go-live; runbooks; monitoring alerts to a named rota | DevOps specialist | Incident outside business hours | Open
R22 | Operational | Backups not restorable when needed | 1 | 5 | 5 | Low | Quarterly restore tests; point-in-time recovery; cross-region copy at enterprise tier | DevOps specialist | Failed restore test | Open
Summary
High | 3
Medium | 14
Low | 5
Open | 22
Average score | 9.8182

## Scoring_Guide
Scoring guide
Use these definitions to keep scores consistent across reviewers.
Score | Likelihood | Impact
1 | Rare: not expected in this project | Negligible: absorbed within the week
2 | Unlikely: could occur | Minor: under one week delay or under 2% cost
3 | Possible: may well occur | Moderate: one to three weeks delay or 2-8% cost
4 | Likely: expected at least once | Major: milestone slip or 8-20% cost; trust affected
5 | Almost certain | Severe: project viability, regulatory breach, or data exposure