## Traceability
Requirements Traceability Matrix
Every requirement in the client's brief traced to design, component, phase, acceptance test and demo step. Status is an input.
Req ID | Requirement (client brief) | Design response (Document 03) | Component | Phase / milestone | Doc 04 acceptance | Acceptance test | Demo step (Doc 12) | Status
R1 | Retrieve specific info from documents on request; controlled access; not open internet | Hybrid retrieval + re-ranking over private corpus; permission filter applied before retrieval; closed-domain system instruction (s.9.2) | Intelligence service, model gateway, PostgreSQL/pgvector | Phase 1 / M1 | s.6 Retrieval | Golden set: source in top results 90%+; permission tests: user without ACL never receives passage | 3.2 step 2 | Planned
R2 | Flag contradictions: different figures, dates or terms for the same thing across documents | Claims ledger with normalisation; cross-document comparison with tolerance; LLM adjudication for terms; findings with both quotes (s.3.3, s.9.1 steps 6-7) | Intelligence service, claims and findings tables | Phase 2 / M2 | s.6 Contradiction detection | Seeded conflicts detected 90%+; false positives under 15%; superseded versions not flagged | 3.2 steps 2-3; seeded issues 1-3 | Planned
R3 | Track missing information: gaps where a decision needs a document or data point not yet provided | Decision checklists (configurable) matched against ledger and inventory; dangling-reference detection (s.9.1 step 8) | Intelligence service, decisions and checklist tables | Phase 2 / M2 | s.6 Gap tracking | All catalogued checklist items evaluated correctly on test decisions; dangling references detected | 3.2 step 4; seeded issues 4-5 | Planned
R4 | Answer management questions in plain language based only on the loaded document set | Grounded generation with citations; independent grounding check; refusal when unsupported; Arabic and English (s.9.2 steps 5-6) | Intelligence service, model gateway, web app | Phase 1 / M1 | s.6 Answer faithfulness; Refusal correctness | Faithfulness 95%+; refusal correctness 90%+; per-language reporting | 3.2 steps 2, 5, 6; seeded issues 6, 8 | Planned
R5 | Closed-domain RAG with verification/audit layer, not a general chatbot | Audit log of every query with retrieved passages and answer; hash-chained events; findings workbench (s.3.2, s.12) | Platform audit log, web app | Phase 1 / M1 | s.6 Security | Audit chain verifies; every query has a logged trace | 3.2 step 11 | Planned
C1 | Three categories: investors; partners/counterparties; customers/members; GCC-specific pipeline | Category-typed relationships; configurable pipelines and stage sets per category; GCC template (s.2.2, s.8.3) | Core API, CRM schema, web app | Phase 1 / M1 | s.6 Reporting (reconciliation) | All three categories and the GCC pipeline demonstrated; stages configurable without code | 3.2 step 7, 10 | Planned
C2 | Contact and relationship records with stage/status tracking | Organisation, Person, Relationship entities; stage history; status values incl. dormant (s.8.3) | Entity registry, CRM schema | Phase 1 / M1 | s.6 Reporting | Record CRUD and stage transitions with history; import of 500-row sample | 3.2 step 7 | Planned
C3 | Follow-up scheduling and reminders | Follow-up tasks with due dates and owners; daily and hourly reminder job to staff; overdue and stale surfacing (s.9.4) | Workers, Core API, web app | Phase 1 / M1 | s.6 Reporting | Reminder generated for due and overdue follow-ups; none sent to external contacts | 3.2 step 7 | Planned
C4 | Any outreach must go through human approval before sending; no fully automated outbound | Outreach Request workflow; four-eyes rule enforced in database; no scheduled-send path; send under approver's authority via connected mailbox; versioned and logged (s.9.3, s.12.3) | Core API, approval policies, mailbox connector, audit log | Phase 2 / M2 | s.6 Approval gate | Automated tests: send without approval fails; drafter cannot approve; audit query shows approver on every send | 3.2 step 8 | Planned
C5 | Basic reporting: who has been contacted, stage, overdue | Dashboards and exports: activity by period, pipeline by stage and category, overdue, dormant, approval turnaround (s.10.1) | Core API reports, web app | Phase 2 / M2 | s.6 Reporting | Dashboard figures reconcile to database counts | 3.2 step 9 | Planned
X1 | Proposed build approach and tools for each system | Documents 03 and 06 | n/a | Proposal | n/a | Client review | First meeting slides 6-12 | Delivered
X2 | Structure that accepts real data later without rebuild | Schema-first with custom fields; configuration-driven rules; import templates; connectors; removable demo data (s.5; Document 07) | Platform, Core API, web app admin | Phase 1-2 / M2 | s.6 Reporting (import) | Custom field and stage added without code; import preview; demo-data removal leaves configuration intact | 3.2 step 10 | Planned
X3 | Timeline to working structure and demo | Document 04: working structure week 6; integrated demo week 8-9 | n/a | Proposal | n/a | Client review | Slide 14 | Delivered
X4 | Cost or pricing model | Documents 05 and 14: run-cost tiers, build effort, three pricing options, 3-year TCO | n/a | Proposal | n/a | Client review | Slides 15-16 | Delivered
N1 | Arabic and English documents, questions, answers and interface (assumed; Document 13 gap 1) | OCR with Arabic; multilingual embeddings; RTL layout; per-language evaluation | Intelligence service, web app | Phase 1-3 | s.6 Answer faithfulness | Arabic golden-set scores within 10 points of English | 3.2 step 5 | Planned
N2 | Data residency by policy (Document 13 gap 2) | Deployment patterns A/B/C; gateway routing by classification (s.3.5) | Model gateway, classification step | Phase 0 decision; Phase 1 build | s.6 Security | Restricted-class document never routed to external provider (gateway log test) | Slide 11 | Planned
N3 | Document version handling (Document 13 gap 5) | Checksum and naming detection; supersedes links; comparison excludes superseded (s.9.1 step 1) | Intelligence service | Phase 2 / M2 | s.6 Contradiction detection | Seeded v1/v2 pair produces no contradiction flag | Seeded issue 3 | Planned
Coverage summary
Planned | 14
In progress | 0
Delivered | 3
Accepted | 0
Deferred | 0
Total | 17